## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 66.7% | 40% | 26.7% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% |  | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 44.1% | 30% | 8.8% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
|  |  |  | Phase 2 | [6 empty] | ←Illustrative
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [7 empty] | Project Financials
| Status Update |  | Challenges
- Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
Community Feedback Highlights
Strong appreciation for transparency and the opportunity to participate in feedback sessions.
Noise complaints from residents in Eastern Section due to nighttime construction.
Planned: 68 miles
Previous Completed: 24 miles
Current Completed: 30 miles
% Completion: 44.1%
Weekly Progress: 6 miles (8.8%)
Allocated Budget: $125M
Current Spend: $90M
Note: Slight overage due to rocky terrain in Eastern Section
Variance: Within 5% over the original projection
Action: Material savings are helping offset unexpected costs
Total Track Installed: 38 mi / 68 mi (55.9%)
Electrification Progress: 30 mi / 68 mi (44.1%) Budget Spent: $90M / $125M projected Overall Status: Minor Delays due to terrain and electrification slippage
4 miles of new track installed in Southeastern Quadrant (now 10/15 mi)
6 miles added to electrification (now 30/68 mi completed)
Community consultation efforts rated highly by participants
Stakeholder Risk: If nighttime work continues, resident dissatisfaction may increase
Procurement Risk: Delays in sourcing electrification components may affect milestone completion
Schedule Risk: Terrain complexity in East remains a persistent constraint